## Hugh
DATE | TOPIC | DETAILS | Time Spent | Challenges faced | Solution
2024-11-12 | Group meeting | Discussed about the topics, datasets and how we working style. | 2 hour | - | -
17/12/2024 | Group meeting | Define the problem statement regarding weather and grain | 2 hour | - | -
18/12/2024 | Data prepared | Found a valid dataset for weather in the USA, started to download daily data for 2022, 2023 | 1 hour | Finding a feature-rich dataset, relevant to our project goals | We found VisualCrossing - A free weather database aimed at data scientists
19/12/2024 | Weather data downloaded | Finished downloading my weather data from visualcrossing.com, took 2 days due to limits on the free account | 2 hour | - | -
20/12/2024 | File combined | Combined the seperate weather files, one for each year 2020-2023, into one main weatherdata.csv file using python and pandas | 1 hour | Using python to manipulate files by importing, merging and then saving them as one file | Easy using the tool Pandas
22/12/2024 | Aquired full crop data | UN cereal production data from 2011 to 2022, need to change weather data to fit | 4 hour | Finding a feature-rich dataset, relevant to my focus | The UN have plenty of crop production databases that are free to use
23/12/2024 | Edit weather data | Removed year 2023 and worked on aquiring future years, 2018 and 2019 | 2 hour | Interacting with visualcrossings web api to download code | Done in browser
25/12/2024 | Aquiring new weather data | Aquired years 2016 and 2017 | 1 hour | Interacting with visualcrossings web api to download code | Done in browser
26/12/2024 | Cereal production data | Proprocessed our UN cereal data and selected United states data only, focusing on the years 2016 to 2022, got weekly crop numbers and prepared to merge with our weather data | 4 hour | - | -
27/12/2024 | Created weather week data | Created new weekly weather df using our weather data for 2016-2022. This will be merged with our new weekly crop numbers | 3 hour | - | -
28/12/2024 | Uploaded data to DB | Uploaded our 3 files to mongoDB. prepared to merge our two weekly files into one master weekly file for future processing | 3 hour | Uploading to mongo db collection | Used MongoDBs Compass tool to import data
29/12/2024 | Merged data in Mongo DB | Merged our weekly crop column into our weekly weather data based on year using mongo | 2 hour | Using query to combine datasets so that weekly crop production is seen on weather data | Used pipeline tool within mongoDB
30/12/2024 | Data Visualisations, preprocessing | Imported data into python. Graphing. Cleaning Data | 4 hour | Graphing stastical details such as distributions | Used Seaborn plotting tool for python for nice graphs
31/12/2024 | ML Algorithms | Implemented random forest regression and Support Vector Regression, Started evaluations | 3 hour | Model performed poorly, showing signs of being overtrained | Changed the testing ratio from 0.2 to 0.3 to reduce overfitting
2025-01-01 | ML Algorithms + Evals | Implemented linear regression model and furtehr evaluations on our 3 models | 2 hour | - | -
2025-02-01 | Project Report | Started work on the project report, finding revelant papers. 449 words in the related work and refrences section about RF regression | 4 hour | Starting report in a manner which all could view and edit | Shared word document in shared folder created by Natalia
2025-03-01 | Methodolgy section | Did work on methodology section in project report. 410 Words. Added refrence. CODE: Added Decision tree regression and Gradient boosting regression to python code for sake of comparisons with other group mebers. | 3 hour | Added more models to project required extensive knowledge of skslearn library | Documentation is available on their website
2025-04-01 | Traveling + Report work | Traveled Home, Worked on report and project journal | 2 hour | - | -

## Natalia
Date | Topic | Description | Time Spent | Challenges faced | Solution
2024-11-12 | Group meeting | Discussed about the topic, Problem statement | 2 hour | NIL | NIL
17/12/2024 | Group meeting | Discussed about the Dataset for the problem statement and deciding on the model. | 2 hour | NIL | NIL
21/12/2024 | Finding Dataset (Weather - India) | Was able to get the India Weather Dataset from visualcrossing.com. Took 3 days to download the data due to data limit for free account. | 1 hour | As it is a group project, each member should have a proper and similar dataset | After searching multiple websites.
22/12/2024 | Finding Dataset (Crop Dataset - India) | Downloaded datasets for crop yield,production and harvested area for the Year 2020- 2023. (Our World in Data- Agricultural Production) | 2 hour | Search for a dataset with required columns and rows | After searching multiple websites.
23/12/2024 | Weather Dataset | Downloaded datasets for Indian weather and crop data for the year 2018-2019 | 1 hour | Because to increase the data points | Downloaded the file
24/12/2024 | Loading the Dataset - Jupyter Notebook | Loaded the weather and crop datasets into Python using Jupyter Notebook. Additionally, Merged the multiple weather datasets into a single dataset. | 2 hour | Unable to merge due to difference in the column datatypes, additional columns. | Apply code and completed the merge.
25/12/2024 | Loading Database - MongoDB | The merged weather dataset, along with the crop dataset, has been loaded into the database separately using MongoDB, creating two separate collections within the same database connection. | 2 hour | NIL | NIL
26/12/2024 | Retrieve Data from Database | The stored data has been retrieved using a MongoDB query and converted into a DataFrame for preprocessing. | 1 hour | NIL | NIL
27/12/2024 | Data Characteristics and Preprocessing | Data characteristics and preprocessing are conducted on the datasets separately (Weather and Crop) to check for missing values, duplicates, and outliers. | 4 hour | NIL | NIL
28/12/2024 | Data Manipulation | Filtered the 2024 weather data since Crop dataset only includes data up to 2023 for consistency between the datasets, which is crucial for analysis and modelling. | 1 hour | The crop dataset contains data from 2018-2023. While the weather weather dataset contains data from 2018-2024 | Removed 2024 data from weather dataset.
29/12/2024 | Data Manipulation and Visualization | Removed outliers and filled null values from both datasets. I also utilized various visualizations (Histogram, Density plot, Box plot,line plot, Pie chart) to understand the distribution of features and the target variable. Additionally, I applied log transformation to the target variable, which was right-skewed. | 2 hour | NIL | NIL
30/12/2024 | Feature Engineering | Merged the datasets and conducted correlation analysis after aggregating the weather features to identify the best-correlated features for the target variable. After this, used MongoDB to store the merged data. Once stored, I retrieved only the necessary features based on the correlation and statistical analysis to prepare for machine learning. | 3 hour | Identifying the highly correlated features with target variable was a little challenging as the dataset contains limited features that correlates well with the target variable | To overcome this challenge, had to aggregate the features before and after the correlation and check for best possible features.
31/12/2024 | Machine Learning Algorithm | Using the selected features and target variable, employed the Random Forest Regressor, Decision Tree and, Gradient Boosting Regressor to assess the model's performance on the chosen dataset. | 3 hour | Tried to implement Linear, logistic and SVM, but the performance of the model was very weak compared to the other tree based models. | Removed it from the code.
2025-01-12 | Evaluation Process | Calculated performance metrics for Random Forest, Decision Tree and, Gradient Boosting Regressor models, comparing their results to identify the best-performing model. Additionally, I visualized the comparison of metrics to provide a clear understanding of each model's effectiveness and accuracy. | 4 hour | I attempted to visualize the yield, production, and harvested area on an India map. However, this was not feasible as the dataset lacks state-wise details, limiting the granularity required for geographical representation. | Used a one-way ANOVA test to analyze the statistical significance of differences among "Area harvested," "Yield," and "Production" data.
2025-02-01 | Evaluation Process | Worked on creating visual representations to analyze yearly trends in area harvested, production, and yield for key crops (Barley, Coconut oil, Coffee, Cotton seed, Groundnut oil, Maize, Millet, Rice, Soyabean, Tea leaves, and Wheat) from 2018 to 2023. The graphs provided a comparative overview of these metrics, helping to identify patterns and variations across crops and years. This analysis aims to support decision-making for resource allocation and agricultural strategy optimization. | 3 hour | NIL | NIL
2025-03-01 | Report - Related works | Started work on report writing for the project - Added content in related works about the Decision Tree algorithm. Also, added the conclusion and future work section. | 3 hour | Future work was a concern. | Dashboards will be tailored to specific regional farming needs, integrating localized data such as crop patterns, weather predictions, and soil conditions
2025-04-01 | Report - Conclusion and Future Work | Added Evaluation metrics for my dataset in the report. | 30 minutes | NIL | NIL
| GitHub | Watched videos to create a github repository and process to upload the files. | 20 minutes | NIL | NIL
| System Requirements file | Created a system requirement file using markdown in Jupyter Notebook. | 1 hour | NIL | NIL
| Output storage - MongoDB | The data for selected grains from 2018 to 2023 has been stored in the MongoDB database, including temperature, humidity, and key metrics like yield, production, and area harvested, for easy comparison and analysis. | 30 minutes | NIL | NIL
2025-05-01 | Creating a video
GitHub - Uploading files

## Wanpin
Date | Topic | Descrption | Time Spent | Operator | Note
2024-11-12 | Group first meeting | Discussed about the topics, datasets and how we working style. | 2 hour | Wanpin | Not totally decided, we will need to make it work later.
17/12/2024 | Group meeting | Define the problem statement with weather and grin | 2 hour | Wanpin | High fever,
18/12/2024 | Data prepared | Start to find the data between weather and stocks price | 2 hour | Wanpin | High fever, 39.9.
19/12/2024 | Data prepared | Weather data downloaded | 3 hour | Wanpin
20/12/2024 | Data prepared | Production data downloaded | 2 hour | Wanpin
23/12/2024 | Data processing | Cleaned the data and combined | 4 hour | Wanpin | Recognizing that the link between broad weather data and the regionality of planting is weak, yield forecasts based on the year are more granular and may require adjustments to research strategies or find the new dataset.
24/12/2024 | Data processing | The dataset is not suitable. The existing weather conditions in the United States are not suitable for planting areas. A new dataset needs to be found. | 4 hour | Wanpin
25/12/2024 | Finding Dataset | The required dataset could not be found | 1 hour | Wanpin
26/12/2024 | Finding Dataset | The required dataset could not be found | 1 hour | Wanpin
27/12/2024 | Finding Dataset | Failed to find the suitable dataset. Changed the crops choice. | 1 hour | Wanpin
28/12/2024 | Finding Dataset Data processing Read related papers | From the existing data set, infer the varieties suitable for planting and find the annual yield data set of the variety. Weather data is 2004-2024. Data cleaning, deal with the missing value and outlier. Created the new features, EDA. | 6 hour | Wanpin
29/12/2024 | Data processing Connect Mongo DB | Continue working in dataset, at the same time, tried to connect to Mango DB. | 2 hour | Wanpin | Feeling unwell, ear infection
30/12/2024 | Data processing | Sick |  | Wanpin | Sick, fever...
31/12/2024 | Data processing | coding for algorithms | 3 hour | Wanpin | Sick
2025-01-01 | Created the Github Repositories | Created the Github Repositories for the project, and invited all the team member as the collaborators. Upload my dataset in the github. Mango DB only connect on local host, so I changed the path retrived the data from github. | 3 hour | Wanpin
2025-02-01 | Data processing/ Evaluation Process | Based on the original topic, I found that my data was not enough to support the research in this area and no results were produced. So I keep my work in coding and also explored the second topic of whether the weather in the region has warmed up in the past 20 years in terms of machine learning based on the weather data package. | 3 hour | Wanpin
2025-03-01 | Project Report | Constructing a report and organizing the findings from the research. | 3 hour | Wanpin
2025-04-01 | Project Report |  | 1 hour | Wanpin
2025-05-01 | Video |  | 3 hour | Wanpin
2025-06-01 | Submission Deadline 9 am

## Moe Ni
Date | Topic | Description
2024-11-12 | Group discussion | discussed about topic and how we will work
17/12/2024 | Group discussion | decided problem statement which is weather and grains to perdict future prices
18/12/2024 | Finding Dataset | explored the dataset in aligement with problem statement
19/12/2024 | Finding Dataset | explored the dataset in aligement with problem statement
20/12/2024 | Group discussion | Modified the problem statement which is prediction grains productions in fucture
| Finding Dataset | found datasets grains production yearly for every regions
21/12/2024 | Finding Dataset | explored mean annual weather datasets for Myanmar
22/12/2024 | Collecting weather dataset | downloaded mean annual weather datasets (1981–2022) from NASA website
23/12/2024 | Modifying data structures | implemented python codes to modifed weather dataframe which requires to meet with project requirements
24/12/2024 | Collecting crop dataset | downloaded crops datasets (1961–2022) from our world in data website and combined sepreated csv files using pandas
25/12/2024 | Creating final dataset | combined three types of datasets such as weather data, yields data and used of land data
27/12/2024 | handling Missing values | explored the solution to hand rest of annual weather data and implemented the code to predict rest of annual weather values using linear regression